## RMMM Tabelle
Risk ID | Category | Risk Description | Probability | Impact | Risk Score | Mitigation Strategy | Indicator | Contingency Plan | Responsible | Status | Last Modified Date
1 | Personel | Personell Shortfall | Low | High | 3 | Upskilling & Training, Taking Time off, Task Reassignment | Personel doesn't know how to solve Programming-Issues, is burned out or doesn't manage to find time to work on the project | Should more knowledge be needed to solve Issues at hand, Training-Ressources will have to be made available and if necessary, one or more Teammembers should provide brief tutoring. In cases of Burnout, a brief timeout should be mandated for the afflicted person. In cases of bad time management, a solution for further proceeding should be discussed in a group forum and if necessary, tasks reassigned. | Samuel B. | Inactive | 2025-04-09
2 | Technical | JW Token | Low | High | 10 | Regenerate secret that is used in the HMAC algorithm of the generation algorithm of the token | Creation of reviews in the name of other users without their knowledge | Temporarily disable login and all endpoints that require authentication (the creation of reviews) until the new secret is generated and implemented | Jonas S. | Inactive | 2025-04-14
3 | Technical | OSM | Low | High | 6 | Cache key map data locally OR implement fallback to another map provider | High response times or failed API requests | Switch to Google Maps API or other Map Provider temporarily | Valentin W. | Inactive | 2025-04-09
4 | Organisatory | Ineffective communication | Low | High | 6 | weekly team meetings, consistent communication channels, document important agreements | unclear task distribution, frequent misunderstandings | Immediate clarification in a dedicated team meeting | Paula K. | Open | 2025-04-09
5 | Time | Unrealistic time-planning | Low | Medium | 3 | Implementation of a sprint workflow, always planning a puffer for each milestone | Goals are not met at the end of sprints, badly implemented/untested solutions due to the time pressure, constant postponing of tasks | checking every second week if tasks are being done in the planned time-frame (sprint review), consulting all team memebers when estimating the needed time for each task, always adding puffer, progress time tracking for more accurate estimation for future tasks and surveillance of the overall project progress | Safae K. | Open | 2025-04-11